## WBS with Gantt Chart
Work Breakdown Structure with Gantt Chart
PROJECT TITLE | Conversational Agent (IMDb bot) | DEVELOPERS | Adrian Morillo
PROJECT MANAGER | Carlos Rueda Carrasco |  | Daniel Elizondo
COMPANY NAME | Group 21 |  | Jose Peña
DATE | 24.02.2020 |  | Will Barlow |  |  |  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR |  |  | PHASE FIVE |  |  | PHASE SIX
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (Expected and Actual) | % of TASK | WEEK 1.1 |  |  | WEEK 1.2 |  |  | WEEK 2.1 |  |  | WEEK 2.2 |  |  | WEEK 3.1 |  |  | WEEK 3.2
[6 empty] | COMPLETE | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | Concept Exploration
1.1 | Project brainstorming | All | 24.02.2020 | 24.02.2020 | 1 hour | 100
1.1.1 | Project topics | All | 24.02.2020 | 24.02.2020 | 2 hours | 100
1.1.2 | Project roles and responsiblities | All | 24.02.2020 | 24.02.2020 | 3 hours | 100
1.2 | Program brainstorming | All | 25.02.2020 | 25.02.2020 | 2 hours | 100
1.2.1 | Choosing project output | All | 25.02.2020 | 25.02.2020 | 2 hours | 100
1.2.2 | Choosing agent type | All | 25.02.2020 | 25.02.2020 | 4 hours | 100
1.3 | Timeline organization | Carlos | 26.02.2020 | 26.02.2020 | 2 hours | 100
1.3.1 | Meeting scheduler | Carlos | 26.02.2020 | 26.02.2020 | 1 hour | 100
1.3.2 | Task/work scheduler | Carlos | 26.02.2020 | 26.02.2020 | 3 hours | 100
2 | System Exploration
2.1 | Group member's skills and capcabilities | All | 27.02.2020 | 27.02.2020 | 1 hour | 100
2.1.1 | Understand personal skills and limitations | Will | 27.02.2020 | 27.02.2020 | 1 hour | 100
2.1.2 | Identify scope of project | Jose, Adrian | 27.02.2020 | 27.02.2020 | 3 hours | 100
2.2 | System software and tools | Jose | 28.02.2020 | 28.02.2020 | 2 hours | 100
2.2.1 | Languages and software used for project | Jose, Adrian, Daniel | 28.02.2020 | 28.02.2020 | 2 hours | 100
2.2.2 | API's and external tools | Daniel, Jose | 28.02.2020 | 28.02.2020 | 2 hours | 100
2.3 | Task allocation | Carlos | 29.02.2020 | 29.02.2020 | 1 hour | 100
2.3.1 | Assign task to each group member | Carlos | 29.02.2020 | 29.02.2020 | 1 hour | 100
2.3.2 | Oragnize WBS accordingly to tasks | Carlos | 29.02.2020 | 29.02.2020 | 3 hours | 100
3 | Requirements
3.1 | Project member requirements | Will | 2.03.2020 | 2.03.2020 | 1 hour | 100
3.1.1 | General project breakdown | Will | 2.03.2020 | 2.03.2020 | 1 hour | 100
3.1.2 | General breaddown of each member requirements to the project | Carlos | 2.03.2020 | 2.03.2020 | 3 hours | 100
3.2 | Software requirements | Jose, Carlos, Adrian | 3.03.2020 | 3.03.2020 | 2 hours | 100
3.2.1 | Software capabilities and scope | Carlos, Jose | 3.03.2020 | 3.03.2020 | 2 hours | 100
3.2.2 | Software limitations and constraints | Carlos, Daniel | 3.03.2020 | 3.03.2020 | 2 hours | 100
3.3 | Conversational agent requirements | Daniel | 4.03.2020 | 4.03.2020 | 2 hours | 100
3.3.1 | Chatbot capabilities and scope | Daniel, Adrian | 4.03.2020 | 4.03.2020 | 2 hours | 100
3.3.2 | Chatbot limitations and contraints | Daniel, Will | 4.03.2020 | 4.03.2020 | 2 hours | 100
4 | Design
4.1 | Project design | Adrian, Carlos | 5.03.2020 | 5.03.2020 | 5 hours | 100
4.1.1 | Design system layout | Adrian, Jose, Carlos | 5.03.2020 | 5.03.2020 | 5 hours | 100
4.1.2 | Design system navigation | Adrian, Jose, Carlos | 5.03.2020 | 5.03.2020 | 5 hours | 100
4.2 | Documentation design | Adrian | 6.03.2020 | 6.03.2020 | 5 hours | 100
4.2.1 | Workload breakdown with WBS and Grantt chart | Adrian, Carlos | 6.03.2020 | 6.03.2020 | 5 hours | 100
4.2.2 | Overall documentation design (all aspects) | Adrian, Carlos | 6.03.2020 | 6.03.2020 | 3 hours | 100
4.3 | Conversational agent design | Adrian | 7.03.2020 | 7.03.2020 | 3 hours | 100
4.3.1 | Chatbot scope | Daniel | 7.03.2020 | 7.03.2020 | 2 hours | 100
4.3.2 | Chatbot navigation (guidelines for responses) | Daniel | 7.03.2020 | 7.03.2020 | 2 hours | 100
5 | Implementation
5.1 | Conversational agent development part1 | Jose | 9.03.2020 | 9.03.2020 | 4 hours | 100
5.1.1 | Data collection | Jose | 9.03.2020 | 9.03.2020 | 2 hours | 100
5.1.2 | Data storage | Will, Jose | 9.03.2020 | 9.03.2020 | 1 hour | 100
5.2 | Conversational agent development part 2 | Daniel, Jose | 10.03.2020 | 10.03.2020 | 3 hours | 100
5.2.1 | Create response arrays/objects/methods | Adrian, Jose | 10.03.2020 | 10.03.2020 | 3 hours | 100
5.2.2 | Compare user input to potenial responses | Daniel, Jose | 10.03.2020 | 10.03.2020 | 3 hours | 100
5.3 | Conversational agent development part3 | Carlos, Adrian ,Jose | 11.03.2020 | 11.03.2020 | 5 hours | 100
5.3.1 | Connect chatbot (java class) with scrapper (java class) | Jose | 11.03.2020 | 11.03.2020 | 4 hours | 100
5.3.2 | Final code check/overall code revision | Jose, Carlos, Daniel | 11.03.2020 | 11.03.2020 | 3 hours | 100
Maintenance
0%
6.1.1 | [5 empty] | 0%
6.1.2 | [5 empty] | 0%
0%
6.2.1 | [5 empty] | 0%
6.2.2 | [5 empty] | 0%
0%
6.3.1 | [5 empty] | 0%
6.3.2 | [5 empty] | 0%